## Dashboard
EdTech Implementation Risk Intelligence System (EIIS)
SEM-Weighted Risk Prioritization Tool ¦ N = 195 Projects ¦ RPI & LA Tech ¦ ARS = P × I × β
| Total Projects |  |  | Critical + High |  | High | Moderate | Low
| 205 |  |  | 14 |  | 14 | 74 | 117
Current SEM β Weights (Update after AMOS run)
| PM → IS β = 0.31 |  | RM → IS β = 0.53 |  | PM → RM γ = 0.62
HOW TO USE THIS TOOL
| 1 | SEM Weights tab — update β values with your final IBM AMOS output. All ARS scores recalculate instantly.
| 2 | Risk Register tab — all 195 real projects pre-loaded with live ARS scores, priorities, and recommended actions.
| 3 | Add new risks in blank rows at the bottom. Select Category from dropdown; P and I scores auto-pull from your data.
| 4 | Risk Heatmap tab — view the ARS matrix showing score ranges for every P × I combination at each β weight.
| 5 | Project Analysis tab — filter and review individual project risk profiles sorted by ARS score.
PRIORITY SUMMARY — ALL 195 PROJECTS
| Priority |  | ARS Range |  | Count (%) | Dominant Pattern | Recommended Response
| Critical |  | ARS > 12 |  | 0 (0.0%) | — | No Critical risks in current dataset
| High |  | 6.0–12.0 |  | 28 (14.4%) | All Delayed outcomes; High complexity | Active mitigation required; assign risk owners
| Moderate |  | 3.0–6.0 |  | 93 (47.7%) | Mix of Delayed and Successful | Periodic monitoring; contingency planning
| Low |  | < 3.0 |  | 74 (37.9%) | Majority Successful outcomes | Accept with monitoring; review at completion

## SEM Weights
SEM-Derived Construct Weights — IBM AMOS Output
Blue cells = user inputs. Update β values with your final AMOS path coefficients. All ARS calculations in the Risk Register update automatically.
⚠ Placeholder β values shown. Replace with actual AMOS standardized path coefficients after running your SEM.
| Construct | Path | β Coefficient | Std. Error | t-value | p-value | 95% CI | Supported?
| Project Management (PM) | PM → IS (Direct) | 0.143 | 0.07 | 4.43 | < 0.001 | [0.17, 0.45] | Yes
| Risk Management (RM) | RM → IS (Direct) | 0.38 | 0.08 | 5.5 | < 0.001 | [0.28, 0.60] | Yes
| PM (Mediated) | PM → RM → IS | 0.27 | 0.06 | 4.5 | < 0.001 | [0.15, 0.41] | Yes
| Project Management | PM → RM | 0.62 | 0.09 | 6.89 | < 0.001 | [0.53, 0.80] | Yes
WEIGHTS APPLIED IN ARS FORMULA — PULL FROM ABOVE
| PM-category risks (β = PM → IS) |  |  |  | 0.143 | Used as weight for all Project Management risks in register
| RM-category risks (β = RM → IS) |  |  |  | 0.38 | Used as weight for all Risk Management risks in register — THIS IS YOUR ARS β

## Risk Register
Risk Register — All 195 EdTech Projects ¦ ARS-Weighted Priorities
ARS = P × I × β ¦ β weights live from SEM Weights sheet ¦ Sorted by ARS (highest first) ¦ Blue cells = user inputs
Total | Critical | High | Moderate | Low | Avg ARS
117 | 0 | 14 | 74 | 117 | 2.661
Project ID | Institution | Project Name | Risk Category | P (Prob) 1–5 | I (Impact) 1–5 | β Weight (SEM) | P × I | ARS (P×I×β) | Priority Tier | Recommended Action | PM Used | Outcome
P195 | LA Tech | Workday Student | Risk Management | 4.27 | 5 | 0.38 | 21.35 | 8.113 | High | Active mitigation planning required; include in project risk register | Yes | Delayed
P053 | RPI | Network services | Risk Management | 4.64 | 4.25 | 0.38 | 19.72 | 7.4936 | High | Active mitigation planning required; include in project risk register | Yes | Delayed
P107 | RPI | Inventions and patents | Risk Management | 3.91 | 5 | 0.38 | 19.55 | 7.429 | High | Active mitigation planning required; include in project risk register | No | Delayed
P155 | RPI | Email Spam filter | Risk Management | 4.27 | 4.5 | 0.38 | 19.215 | 7.3017 | High | Active mitigation planning required; include in project risk register | Yes | Delayed
P049 | RPI | Backups | Risk Management | 3.91 | 4.75 | 0.38 | 18.5725 | 7.0576 | High | Active mitigation planning required; include in project risk register | Yes | Delayed
P010 | RPI | Parking Management System | Risk Management | 4.27 | 4.25 | 0.38 | 18.1475 | 6.896 | High | Active mitigation planning required; include in project risk register | No | Delayed
P076 | RPI | Payment processing Software (check printing) | Risk Management | 3.55 | 5 | 0.38 | 17.75 | 6.745 | High | Active mitigation planning required; include in project risk register | Yes | Delayed
P136 | RPI | Interlibrary loan and document delivery syste | Risk Management | 3.55 | 5 | 0.38 | 17.75 | 6.745 | High | Active mitigation planning required; include in project risk register | No | Delayed
P122 | RPI | Package Tracking System | Risk Management | 3.55 | 5 | 0.38 | 17.75 | 6.745 | High | Active mitigation planning required; include in project risk register | Yes | Delayed
P142 | RPI | Data Warehouse Business Intelligence and Anal | Risk Management | 3.91 | 4.5 | 0.38 | 17.595 | 6.6861 | High | Active mitigation planning required; include in project risk register | Yes | Delayed
P110 | RPI | Intellectual Property | Risk Management | 5 | 3.5 | 0.38 | 17.5 | 6.65 | High | Active mitigation planning required; include in project risk register | Yes | Failed
P041 | RPI | Wireless network management | Risk Management | 3.55 | 4.75 | 0.38 | 16.8625 | 6.4078 | High | Active mitigation planning required; include in project risk register | Yes | Delayed
P115 | RPI | Major Gift Fundraising Software | Risk Management | 3.91 | 4.25 | 0.38 | 16.6175 | 6.3147 | High | Active mitigation planning required; include in project risk register | Yes | Delayed
P075 | RPI | Alumni collaboration | Risk Management | 3.55 | 4.5 | 0.38 | 15.975 | 6.0705 | High | Active mitigation planning required; include in project risk register | Yes | Delayed
P158 | RPI | *Need description from Bursar office* | Risk Management | 3.91 | 4 | 0.38 | 15.64 | 5.9432 | Moderate | Periodic monitoring; develop contingency plan at next milestone | Yes | Delayed
P161 | RPI | Comromised account reporting service | Organizational Readiness | 3.18 | 4.75 | 0.38 | 15.105 | 5.7399 | Moderate | Periodic monitoring; develop contingency plan at next milestone | Yes | Delayed
P026 | RPI | Benefits management. Employee & HR Portals | Risk Management | 3.55 | 4.25 | 0.38 | 15.0875 | 5.7332 | Moderate | Periodic monitoring; develop contingency plan at next milestone | Yes | Delayed
P159 | RPI | Customer communication platform for transacti | Risk Management | 3.55 | 4.25 | 0.38 | 15.0875 | 5.7332 | Moderate | Periodic monitoring; develop contingency plan at next milestone | No | Delayed
P112 | RPI | Procurement messaging connector | Risk Management | 3.55 | 4.25 | 0.38 | 15.0875 | 5.7332 | Moderate | Periodic monitoring; develop contingency plan at next milestone | Yes | Delayed
P006 | RPI | Digital asset management system | Risk Management | 4.27 | 3.5 | 0.38 | 14.945 | 5.6791 | Moderate | Periodic monitoring; develop contingency plan at next milestone | No | Delayed
P096 | RPI | Internships and job placement | Risk Management | 4.27 | 3.5 | 0.38 | 14.945 | 5.6791 | Moderate | Periodic monitoring; develop contingency plan at next milestone | Yes | Delayed
P015 | RPI | Digital asset management system for archives | Risk Management | 3.91 | 3.75 | 0.38 | 14.6625 | 5.5718 | Moderate | Periodic monitoring; develop contingency plan at next milestone | No | Delayed
P135 | RPI | Web Proxy service | Risk Management | 3.55 | 4 | 0.38 | 14.2 | 5.396 | Moderate | Periodic monitoring; develop contingency plan at next milestone | No | Delayed
P019 | RPI | Logging attendance at events with ID Card rea | Risk Management | 3.55 | 4 | 0.38 | 14.2 | 5.396 | Moderate | Periodic monitoring; develop contingency plan at next milestone | No | Delayed
P121 | RPI | Weather Sentry system | Risk Management | 4.64 | 3 | 0.38 | 13.92 | 5.2896 | Moderate | Periodic monitoring; develop contingency plan at next milestone | No | Delayed
P095 | RPI | Secondary authoritative DNS (external) | Risk Management | 4.27 | 3.25 | 0.38 | 13.8775 | 5.2734 | Moderate | Periodic monitoring; develop contingency plan at next milestone | Yes | Delayed
P151 | RPI | Health Center software | Risk Management | 3.91 | 3.5 | 0.38 | 13.685 | 5.2003 | Moderate | Periodic monitoring; develop contingency plan at next milestone | Yes | Delayed
P192 | RPI | Project Management | Risk Management | 3.91 | 3.5 | 0.38 | 13.685 | 5.2003 | Moderate | Periodic monitoring; develop contingency plan at next milestone | No | Delayed
P101 | RPI | Imaging and Document Management, Workflow – t | Organizational Readiness | 3.18 | 4.25 | 0.38 | 13.515 | 5.1357 | Moderate | Periodic monitoring; develop contingency plan at next milestone | Yes | Delayed
P106 | RPI | Java integrated development environment | Organizational Readiness | 2.82 | 4.75 | 0.38 | 13.395 | 5.0901 | Moderate | Periodic monitoring; develop contingency plan at next milestone | Yes | Delayed
P091 | RPI | because Microsoft Live is not effective when | Organizational Readiness | 2.82 | 4.75 | 0.38 | 13.395 | 5.0901 | Moderate | Periodic monitoring; develop contingency plan at next milestone | No | Delayed
P183 | RPI | Campuscard.rpi.edu – ID Card, RAD, POS – Tran | Risk Management | 3.55 | 3.75 | 0.38 | 13.3125 | 5.0587 | Moderate | Periodic monitoring; develop contingency plan at next milestone | Yes | Delayed
P077 | RPI | Email | Risk Management | 3.55 | 3.75 | 0.38 | 13.3125 | 5.0587 | Moderate | Periodic monitoring; develop contingency plan at next milestone | Yes | Delayed
P132 | RPI | Service and infrastructure monitoring | Risk Management | 4.27 | 3 | 0.38 | 12.81 | 4.8678 | Moderate | Periodic monitoring; develop contingency plan at next milestone | Yes | Delayed
P140 | RPI | Authentication | Organizational Readiness | 3.18 | 4 | 0.38 | 12.72 | 4.8336 | Moderate | Periodic monitoring; develop contingency plan at next milestone | Yes | Delayed
P002 | RPI | used for IPEDS/common data set | Risk Management | 3.91 | 3.25 | 0.38 | 12.7075 | 4.8289 | Moderate | Periodic monitoring; develop contingency plan at next milestone | No | Delayed
P144 | RPI | Talent management | Risk Management | 3.55 | 3.5 | 0.38 | 12.425 | 4.7215 | Moderate | Periodic monitoring; develop contingency plan at next milestone | Yes | Delayed
P166 | RPI | Business Communication Platform | Organizational Readiness | 3.18 | 3.75 | 0.38 | 11.925 | 4.5315 | Moderate | Periodic monitoring; develop contingency plan at next milestone | No | Delayed
P152 | RPI | Survey platform | Project Management | 3.18 | 3.75 | 0.143 | 11.925 | 1.7053 | Low | Accept with monitoring; review at project completion | Yes | Delayed
P168 | RPI | *need more information* | Risk Management | 4.27 | 2.75 | 0.38 | 11.7425 | 4.4622 | Moderate | Periodic monitoring; develop contingency plan at next milestone | No | Delayed
P128 | RPI | project management platform | Risk Management | 4.64 | 2.5 | 0.38 | 11.6 | 4.408 | Moderate | Periodic monitoring; develop contingency plan at next milestone | Yes | Delayed
P186 | RPI | Backups | Organizational Readiness | 2.82 | 4 | 0.38 | 11.28 | 4.2864 | Moderate | Periodic monitoring; develop contingency plan at next milestone | No | Delayed
P167 | RPI | polling platform | Organizational Readiness | 3.18 | 3.5 | 0.38 | 11.13 | 4.2294 | Moderate | Periodic monitoring; develop contingency plan at next milestone | Yes | Delayed
P074 | RPI | Student education -can we expand? | Organizational Readiness | 3.18 | 3.5 | 0.38 | 11.13 | 4.2294 | Moderate | Periodic monitoring; develop contingency plan at next milestone | Yes | Delayed
P178 | RPI | Graduate Admissions and inquiries | Organizational Readiness | 2.45 | 4.5 | 0.38 | 11.025 | 4.1895 | Moderate | Periodic monitoring; develop contingency plan at next milestone | No | Successful
P022 | RPI | Batch scheduler integrated with Banner | Risk Management | 3.91 | 2.75 | 0.38 | 10.7525 | 4.086 | Moderate | Periodic monitoring; develop contingency plan at next milestone | Yes | Delayed
P114 | RPI | Mathematical Computation | Risk Management | 4.27 | 2.5 | 0.38 | 10.675 | 4.0565 | Moderate | Periodic monitoring; develop contingency plan at next milestone | Yes | Delayed
P072 | RPI | Event, Venue and Catering Management | Risk Management | 4.27 | 2.5 | 0.38 | 10.675 | 4.0565 | Moderate | Periodic monitoring; develop contingency plan at next milestone | Yes | Delayed
P056 | RPI | online schedule tool | Risk Management | 4.27 | 2.5 | 0.38 | 10.675 | 4.0565 | Moderate | Periodic monitoring; develop contingency plan at next milestone | Yes | Delayed
P020 | RPI | Replacement for Arts Management/Theatre Manag | Risk Management | 3.55 | 3 | 0.38 | 10.65 | 4.047 | Moderate | Periodic monitoring; develop contingency plan at next milestone | Yes | Delayed
P134 | RPI | Imaging and Document Management | Risk Management | 3.55 | 3 | 0.38 | 10.65 | 4.047 | Moderate | Periodic monitoring; develop contingency plan at next milestone | Yes | Delayed
P087 | RPI | *need more information* | Project Management | 2.82 | 3.75 | 0.143 | 10.575 | 1.5122 | Low | Accept with monitoring; review at project completion | No | Delayed
P040 | RPI | Used to deliver phone calls to the desktops/l | Project Management | 2.82 | 3.75 | 0.143 | 10.575 | 1.5122 | Low | Accept with monitoring; review at project completion | Yes | Delayed
P065 | RPI | Campus mobile apps | Project Management | 2.82 | 3.75 | 0.143 | 10.575 | 1.5122 | Low | Accept with monitoring; review at project completion | Yes | Delayed
P193 | RPI | IT Services and Support Center | Organizational Readiness | 2.82 | 3.75 | 0.38 | 10.575 | 4.0185 | Moderate | Periodic monitoring; develop contingency plan at next milestone | No | Delayed
P130 | RPI | Material Safety Data Sheets | Organizational Readiness | 2.82 | 3.75 | 0.38 | 10.575 | 4.0185 | Moderate | Periodic monitoring; develop contingency plan at next milestone | Yes | Delayed
P127 | RPI | curriculum proposals | Organizational Readiness | 2.09 | 5 | 0.38 | 10.45 | 3.971 | Moderate | Periodic monitoring; develop contingency plan at next milestone | Yes | Successful
P180 | RPI | International Study, SEVIS Reporting | Organizational Readiness | 2.45 | 4.25 | 0.38 | 10.4125 | 3.9568 | Moderate | Periodic monitoring; develop contingency plan at next milestone | No | Successful
P088 | RPI | Hosting for software development | Organizational Readiness | 3.18 | 3.25 | 0.38 | 10.335 | 3.9273 | Moderate | Periodic monitoring; develop contingency plan at next milestone | Yes | Delayed
P129 | RPI | Texting Platform | Organizational Readiness | 2.82 | 3.5 | 0.38 | 9.87 | 3.7506 | Moderate | Periodic monitoring; develop contingency plan at next milestone | Yes | Delayed
P123 | RPI | Enterprise Email (On prem) | Organizational Readiness | 2.82 | 3.5 | 0.38 | 9.87 | 3.7506 | Moderate | Periodic monitoring; develop contingency plan at next milestone | Yes | Delayed
P169 | RPI | Spam/malware detection/rejection | Project Management | 2.82 | 3.5 | 0.143 | 9.87 | 1.4114 | Low | Accept with monitoring; review at project completion | Yes | Delayed
P051 | RPI | Health and dependent care reimbursement | Project Management | 2.82 | 3.5 | 0.143 | 9.87 | 1.4114 | Low | Accept with monitoring; review at project completion | Yes | Delayed
P043 | RPI | VoIP; Campus telephones | Organizational Readiness | 2.82 | 3.5 | 0.38 | 9.87 | 3.7506 | Moderate | Periodic monitoring; develop contingency plan at next milestone | Yes | Delayed
P016 | RPI | Digital preservation | Organizational Readiness | 2.82 | 3.5 | 0.38 | 9.87 | 3.7506 | Moderate | Periodic monitoring; develop contingency plan at next milestone | Yes | Delayed
P067 | RPI | Student Information System (SIS) Rensselaer S | Organizational Readiness | 2.45 | 4 | 0.38 | 9.8 | 3.724 | Moderate | Periodic monitoring; develop contingency plan at next milestone | Yes | Successful
P113 | RPI | email marketing platform | Risk Management | 3.91 | 2.5 | 0.38 | 9.775 | 3.7145 | Moderate | Periodic monitoring; develop contingency plan at next milestone | Yes | Delayed
P009 | RPI | Confidential Payroll processing | Risk Management | 3.55 | 2.75 | 0.38 | 9.7625 | 3.7097 | Moderate | Periodic monitoring; develop contingency plan at next milestone | No | Delayed
P118 | RPI | Student Intervention and Judicial System | Risk Management | 3.55 | 2.75 | 0.38 | 9.7625 | 3.7097 | Moderate | Periodic monitoring; develop contingency plan at next milestone | Yes | Delayed
P170 | RPI | Platform for building path-finders to discipl | Risk Management | 3.55 | 2.75 | 0.38 | 9.7625 | 3.7097 | Moderate | Periodic monitoring; develop contingency plan at next milestone | Yes | Delayed
P071 | RPI | Dig Safely NY compliance | Project Management | 3.18 | 3 | 0.143 | 9.54 | 1.3642 | Low | Accept with monitoring; review at project completion | Yes | Delayed
P048 | RPI | Monitoring system for Campus Code Blue phones | Project Management | 3.18 | 3 | 0.143 | 9.54 | 1.3642 | Low | Accept with monitoring; review at project completion | Yes | Delayed
P173 | RPI | survey tool | Project Management | 2.45 | 3.75 | 0.143 | 9.1875 | 1.3138 | Low | Accept with monitoring; review at project completion | Yes | Successful
P094 | RPI | IA - AI dashboard tool for AOs | Organizational Readiness | 2.45 | 3.75 | 0.38 | 9.1875 | 3.4912 | Moderate | Periodic monitoring; develop contingency plan at next milestone | Yes | Successful
P154 | RPI | Site license for administrative and research | Project Management | 2.82 | 3.25 | 0.143 | 9.165 | 1.3106 | Low | Accept with monitoring; review at project completion | Yes | Delayed
P031 | RPI | marketing tool | Organizational Readiness | 2.82 | 3.25 | 0.38 | 9.165 | 3.4827 | Moderate | Periodic monitoring; develop contingency plan at next milestone | No | Delayed
P062 | RPI | ERP (Enterprise Resource Planning) TPS- Main | Organizational Readiness | 2.82 | 3.25 | 0.38 | 9.165 | 3.4827 | Moderate | Periodic monitoring; develop contingency plan at next milestone | No | Delayed
P187 | RPI | Chemical Tracking System | Organizational Readiness | 2.09 | 4.25 | 0.38 | 8.8825 | 3.3754 | Moderate | Periodic monitoring; develop contingency plan at next milestone | Yes | Successful
P081 | RPI |  | Risk Management | 3.55 | 2.5 | 0.38 | 8.875 | 3.3725 | Moderate | Periodic monitoring; develop contingency plan at next milestone | Yes | Delayed
P021 | RPI | Public Safety Voice Recording System | Risk Management | 3.55 | 2.5 | 0.38 | 8.875 | 3.3725 | Moderate | Periodic monitoring; develop contingency plan at next milestone | Yes | Delayed
P105 | RPI | Space Management | Risk Management | 3.55 | 2.5 | 0.38 | 8.875 | 3.3725 | Moderate | Periodic monitoring; develop contingency plan at next milestone | Yes | Delayed
P147 | RPI | Postal System | Risk Management | 3.55 | 2.5 | 0.38 | 8.875 | 3.3725 | Moderate | Periodic monitoring; develop contingency plan at next milestone | No | Delayed
P082 | RPI | View/Purchase course materials from the LMS V | Risk Management | 3.91 | 2.25 | 0.38 | 8.7975 | 3.343 | Moderate | Periodic monitoring; develop contingency plan at next milestone | No | Delayed
P138 | RPI | Card Access ID Access; Campus Security – door | Organizational Readiness | 3.18 | 2.75 | 0.38 | 8.745 | 3.3231 | Moderate | Periodic monitoring; develop contingency plan at next milestone | No | Delayed
P184 | RPI | Online meal ordering system | Organizational Readiness | 3.18 | 2.75 | 0.38 | 8.745 | 3.3231 | Moderate | Periodic monitoring; develop contingency plan at next milestone | Yes | Delayed
P084 | RPI | View course material from the course catalog | Organizational Readiness | 3.18 | 2.75 | 0.38 | 8.745 | 3.3231 | Moderate | Periodic monitoring; develop contingency plan at next milestone | Yes | Delayed
P028 | RPI | LMS (Learning Mgmt System) | Organizational Readiness | 3.18 | 2.75 | 0.38 | 8.745 | 3.3231 | Moderate | Periodic monitoring; develop contingency plan at next milestone | No | Delayed
P079 | RPI | Load Balancing | Organizational Readiness | 3.18 | 2.75 | 0.38 | 8.745 | 3.3231 | Moderate | Periodic monitoring; develop contingency plan at next milestone | Yes | Delayed
P120 | RPI | Institutional Research compliance management | Organizational Readiness | 3.18 | 2.75 | 0.38 | 8.745 | 3.3231 | Moderate | Periodic monitoring; develop contingency plan at next milestone | Yes | Delayed
P080 | RPI | Process Management | Organizational Readiness | 3.18 | 2.75 | 0.38 | 8.745 | 3.3231 | Moderate | Periodic monitoring; develop contingency plan at next milestone | Yes | Delayed
P185 | RPI | Project management tool | Organizational Readiness | 2.45 | 3.5 | 0.38 | 8.575 | 3.2585 | Moderate | Periodic monitoring; develop contingency plan at next milestone | Yes | Successful
P066 | RPI | Supplier Management | Organizational Readiness | 2.45 | 3.5 | 0.38 | 8.575 | 3.2585 | Moderate | Periodic monitoring; develop contingency plan at next milestone | Yes | Successful
P023 | RPI | Infrastructure as a Service | Organizational Readiness | 2.45 | 3.5 | 0.38 | 8.575 | 3.2585 | Moderate | Periodic monitoring; develop contingency plan at next milestone | Yes | Successful
P139 | RPI | LMS | Project Management | 2.45 | 3.5 | 0.143 | 8.575 | 1.2262 | Low | Accept with monitoring; review at project completion | Yes | Successful
P030 | RPI | Cloud storage | Organizational Readiness | 2.82 | 3 | 0.38 | 8.46 | 3.2148 | Moderate | Periodic monitoring; develop contingency plan at next milestone | Yes | Delayed
P160 | RPI | Mail Transport Agent | Project Management | 2.82 | 3 | 0.143 | 8.46 | 1.2098 | Low | Accept with monitoring; review at project completion | No | Delayed
P013 | RPI | Laboratory Information Management System – CO | Project Management | 2.09 | 4 | 0.143 | 8.36 | 1.1955 | Low | Accept with monitoring; review at project completion | No | Successful
P045 | RPI | Research Compliance Training | Risk Management | 3.55 | 2.25 | 0.38 | 7.9875 | 3.0353 | Moderate | Periodic monitoring; develop contingency plan at next milestone | Yes | Delayed
P069 | RPI | Identity database for Office 365 | Risk Management | 3.55 | 2.25 | 0.38 | 7.9875 | 3.0353 | Moderate | Periodic monitoring; develop contingency plan at next milestone | No | Delayed
P034 | RPI | Digital Signage | Risk Management | 3.55 | 2.25 | 0.38 | 7.9875 | 3.0353 | Moderate | Periodic monitoring; develop contingency plan at next milestone | No | Delayed
P012 | RPI | Constituent communication | Project Management | 3.18 | 2.5 | 0.143 | 7.95 | 1.1368 | Low | Accept with monitoring; review at project completion | Yes | Delayed
P024 | RPI | Infrastructure as a Service | Organizational Readiness | 3.18 | 2.5 | 0.38 | 7.95 | 3.021 | Moderate | Periodic monitoring; develop contingency plan at next milestone | Yes | Delayed
P007 | RPI | Identity database for Windows | Organizational Readiness | 2.09 | 3.75 | 0.38 | 7.8375 | 2.9782 | Low | Accept with monitoring; review at project completion | No | Successful
P164 | RPI | IDM - Custom Applications | Project Management | 2.09 | 3.75 | 0.143 | 7.8375 | 1.1208 | Low | Accept with monitoring; review at project completion | Yes | Successful
P052 | RPI | Email Storage | Project Management | 2.09 | 3.75 | 0.143 | 7.8375 | 1.1208 | Low | Accept with monitoring; review at project completion | Yes | Successful
P090 | RPI | Extron control system monitoring system | Project Management | 2.09 | 3.75 | 0.143 | 7.8375 | 1.1208 | Low | Accept with monitoring; review at project completion | Yes | Successful
P145 | RPI | Hosting of campus websites | Risk Management | 3.91 | 2 | 0.38 | 7.82 | 2.9716 | Low | Accept with monitoring; review at project completion | Yes | Delayed
P001 | RPI | Budget Planning | Project Management | 2.82 | 2.75 | 0.143 | 7.755 | 1.109 | Low | Accept with monitoring; review at project completion | Yes | Delayed
P182 | RPI | Oracle DB development and management | Organizational Readiness | 2.82 | 2.75 | 0.38 | 7.755 | 2.9469 | Low | Accept with monitoring; review at project completion | Yes | Delayed
P035 | RPI | SSO, Authentication | Organizational Readiness | 2.82 | 2.75 | 0.38 | 7.755 | 2.9469 | Low | Accept with monitoring; review at project completion | No | Delayed
P003 | RPI | Access database used by Registrar Office | Organizational Readiness | 2.45 | 3 | 0.38 | 7.35 | 2.793 | Low | Accept with monitoring; review at project completion | No | Successful
P005 | RPI | Capital Project Tracking System | Project Management | 2.45 | 3 | 0.143 | 7.35 | 1.0511 | Low | Accept with monitoring; review at project completion | Yes | Successful
P029 | RPI | Leadership collaboration | Project Management | 2.45 | 3 | 0.143 | 7.35 | 1.0511 | Low | Accept with monitoring; review at project completion | No | Successful
P057 | RPI | Compromised account reporting service | Organizational Readiness | 2.45 | 3 | 0.38 | 7.35 | 2.793 | Low | Accept with monitoring; review at project completion | No | Successful
P126 | RPI | content management and knowledge management t | Organizational Readiness | 2.09 | 3.5 | 0.38 | 7.315 | 2.7797 | Low | Accept with monitoring; review at project completion | Yes | Successful
P063 | RPI | Workflow engine | Organizational Readiness | 2.09 | 3.5 | 0.38 | 7.315 | 2.7797 | Low | Accept with monitoring; review at project completion | Yes | Successful
P141 | RPI | web-based IDE | Project Management | 2.09 | 3.5 | 0.143 | 7.315 | 1.046 | Low | Accept with monitoring; review at project completion | No | Successful
P104 | RPI | DW ETL (Extraction, Transformation, and Loadi | Project Management | 3.18 | 2.25 | 0.143 | 7.155 | 1.0232 | Low | Accept with monitoring; review at project completion | Yes | Delayed
P097 | RPI | Compromised account reporting service | Project Management | 3.18 | 2.25 | 0.143 | 7.155 | 1.0232 | Low | Accept with monitoring; review at project completion | Yes | Delayed
P149 | RPI | Database | Project Management | 2.82 | 2.5 | 0.143 | 7.05 | 1.0081 | Low | Accept with monitoring; review at project completion | Yes | Delayed
P060 | RPI | Wi-fi authentication | Organizational Readiness | 2.82 | 2.5 | 0.38 | 7.05 | 2.679 | Low | Accept with monitoring; review at project completion | No | Delayed
P179 | RPI | Telephone and workorder billing system | Organizational Readiness | 2.45 | 2.75 | 0.38 | 6.7375 | 2.5603 | Low | Accept with monitoring; review at project completion | Yes | Successful
P194 | RPI | Video Conferencing | Organizational Readiness | 2.45 | 2.75 | 0.38 | 6.7375 | 2.5603 | Low | Accept with monitoring; review at project completion | No | Successful
P070 | RPI | credit check | Organizational Readiness | 2.45 | 2.75 | 0.38 | 6.7375 | 2.5603 | Low | Accept with monitoring; review at project completion | Yes | Successful
P039 | RPI | Campus firewall | Project Management | 3.18 | 2 | 0.143 | 6.36 | 0.90948 | Low | Accept with monitoring; review at project completion | Yes | Delayed
P100 | RPI | *need more information* | Organizational Readiness | 2.82 | 2.25 | 0.38 | 6.345 | 2.4111 | Low | Accept with monitoring; review at project completion | Yes | Delayed
P165 | RPI | Online Learning Management | Project Management | 2.82 | 2.25 | 0.143 | 6.345 | 0.90733 | Low | Accept with monitoring; review at project completion | Yes | Delayed
P033 | RPI | Learning Management System | Project Management | 2.82 | 2.25 | 0.143 | 6.345 | 0.90733 | Low | Accept with monitoring; review at project completion | Yes | Delayed
P059 | RPI | Research machining support | Project Management | 2.09 | 3 | 0.143 | 6.27 | 0.89661 | Low | Accept with monitoring; review at project completion | Yes | Successful
P174 | RPI | Mailing list manager (MLM) | Risk Management | 3.55 | 1.75 | 0.38 | 6.2125 | 2.3607 | Low | Accept with monitoring; review at project completion | Yes | Delayed
P068 | RPI | Classroom and Ad-hoc room scheduling | Organizational Readiness | 2.45 | 2.5 | 0.38 | 6.125 | 2.3275 | Low | Accept with monitoring; review at project completion | Yes | Successful
P117 | RPI | Mathematical Modeling and Analysis | Organizational Readiness | 2.45 | 2.5 | 0.38 | 6.125 | 2.3275 | Low | Accept with monitoring; review at project completion | Yes | Successful
P190 | RPI | Media Operation Scheduling | Project Management | 2.45 | 2.5 | 0.143 | 6.125 | 0.87587 | Low | Accept with monitoring; review at project completion | Yes | Successful
P058 | RPI | Web development platform | Organizational Readiness | 1.36 | 4.5 | 0.38 | 6.12 | 2.3256 | Low | Accept with monitoring; review at project completion | Yes | Successful
P018 | RPI | Public Safety Dispatch System | Organizational Readiness | 1.73 | 3.5 | 0.38 | 6.055 | 2.3009 | Low | Accept with monitoring; review at project completion | Yes | Successful
P085 | RPI | a workplace productivity platform that lets o | Risk Management | 3.91 | 1.5 | 0.38 | 5.865 | 2.2287 | Low | Accept with monitoring; review at project completion | Yes | Delayed
P131 | RPI | A software database for journalists and publi | Risk Management | 3.91 | 1.5 | 0.38 | 5.865 | 2.2287 | Low | Accept with monitoring; review at project completion | Yes | Delayed
P078 | RPI | Monitoring and communication to classroom, me | Organizational Readiness | 2.09 | 2.75 | 0.38 | 5.7475 | 2.1841 | Low | Accept with monitoring; review at project completion | No | Successful
P014 | RPI | AI tool for reviewing travel reports and AP I | Project Management | 2.09 | 2.75 | 0.143 | 5.7475 | 0.82189 | Low | Accept with monitoring; review at project completion | Yes | Successful
P032 | RPI | Scholarship Management | Project Management | 2.82 | 2 | 0.143 | 5.64 | 0.80652 | Low | Accept with monitoring; review at project completion | No | Delayed
P011 | RPI | eInvoicing, vPayment | Project Management | 2.82 | 2 | 0.143 | 5.64 | 0.80652 | Low | Accept with monitoring; review at project completion | Yes | Delayed
P124 | RPI | Microsoft Office Tools/Campus License | Organizational Readiness | 1.73 | 3.25 | 0.38 | 5.6225 | 2.1365 | Low | Accept with monitoring; review at project completion | Yes | Successful
P050 | RPI | Travel and Expense Mgmt | Project Management | 3.18 | 1.75 | 0.143 | 5.565 | 0.7958 | Low | Accept with monitoring; review at project completion | Yes | Delayed
P143 | RPI | Oracle Enterprise Management | Project Management | 3.18 | 1.75 | 0.143 | 5.565 | 0.7958 | Low | Accept with monitoring; review at project completion | No | Delayed
P036 | RPI | Payments | Project Management | 2.45 | 2.25 | 0.143 | 5.5125 | 0.78829 | Low | Accept with monitoring; review at project completion | Yes | Successful
P054 | RPI | an instant messaging and VoIP social platform | Organizational Readiness | 2.45 | 2.25 | 0.38 | 5.5125 | 2.0947 | Low | Accept with monitoring; review at project completion | Yes | Successful
P017 | RPI | Finding aids and accession records | Project Management | 2.45 | 2.25 | 0.143 | 5.5125 | 0.78829 | Low | Accept with monitoring; review at project completion | No | Successful
P025 | RPI | Institute Calendaring | Organizational Readiness | 2.45 | 2.25 | 0.38 | 5.5125 | 2.0947 | Low | Accept with monitoring; review at project completion | Yes | Successful
P098 | RPI | Heartland ECSI is a company approved by the g | Organizational Readiness | 2.45 | 2.25 | 0.38 | 5.5125 | 2.0947 | Low | Accept with monitoring; review at project completion | No | Successful
P119 | RPI | Web Streaming and Cataloging Platform for cou | Organizational Readiness | 2.45 | 2.25 | 0.38 | 5.5125 | 2.0947 | Low | Accept with monitoring; review at project completion | No | Successful
P108 | RPI | Inventions and patents **being replaced by In | Project Management | 2.45 | 2.25 | 0.143 | 5.5125 | 0.78829 | Low | Accept with monitoring; review at project completion | Yes | Successful
P044 | RPI | Voicemail | Risk Management | 4.27 | 1.25 | 0.38 | 5.3375 | 2.0282 | Low | Accept with monitoring; review at project completion | No | Delayed
P125 | RPI | data visualization software | Project Management | 2.09 | 2.5 | 0.143 | 5.225 | 0.74717 | Low | Accept with monitoring; review at project completion | Yes | Successful
P038 | RPI | Multi-factor authentication | Organizational Readiness | 2.09 | 2.5 | 0.38 | 5.225 | 1.9855 | Low | Accept with monitoring; review at project completion | No | Successful
P092 | RPI | Classroom management, Assessment and Grading | Project Management | 2.09 | 2.5 | 0.143 | 5.225 | 0.74717 | Low | Accept with monitoring; review at project completion | No | Successful
P064 | RPI | Degree Works Planning/Degree Clearance | Organizational Readiness | 2.09 | 2.5 | 0.38 | 5.225 | 1.9855 | Low | Accept with monitoring; review at project completion | Yes | Successful
P027 | RPI | a URL shortening service and a link managemen | Organizational Readiness | 2.09 | 2.5 | 0.38 | 5.225 | 1.9855 | Low | Accept with monitoring; review at project completion | Yes | Successful
P046 | RPI | On Premisely hosted campus applications | Project Management | 2.09 | 2.5 | 0.143 | 5.225 | 0.74717 | Low | Accept with monitoring; review at project completion | Yes | Successful
P133 | RPI | Transcripts used by Registrar and OIRA | Organizational Readiness | 1.73 | 3 | 0.38 | 5.19 | 1.9722 | Low | Accept with monitoring; review at project completion | Yes | Successful
P137 | RPI | Integrated library management system (catalog | Organizational Readiness | 1.36 | 3.75 | 0.38 | 5.1 | 1.938 | Low | Accept with monitoring; review at project completion | Yes | Successful
P111 | RPI | A labor market analytics company that provide | Project Management | 2.45 | 2 | 0.143 | 4.9 | 0.7007 | Low | Accept with monitoring; review at project completion | No | Successful
P157 | RPI | Storage/computing | Project Management | 2.45 | 2 | 0.143 | 4.9 | 0.7007 | Low | Accept with monitoring; review at project completion | Yes | Successful
P163 | RPI | Security Information and event Management | Organizational Readiness | 1.73 | 2.75 | 0.38 | 4.7575 | 1.8079 | Low | Accept with monitoring; review at project completion | Yes | Successful
P004 | RPI | The Facilities Operations Customer Service Ce | Organizational Readiness | 2.09 | 2.25 | 0.38 | 4.7025 | 1.7869 | Low | Accept with monitoring; review at project completion | Yes | Successful
P109 | RPI | Procure-to-Pay; OSCAR: Workflow; Access to Ba | Risk Management | 4.64 | 1 | 0.38 | 4.64 | 1.7632 | Low | Accept with monitoring; review at project completion | Yes | Delayed
P083 | RPI | View/purchase course materials during registr | Project Management | 2.45 | 1.75 | 0.143 | 4.2875 | 0.61311 | Low | Accept with monitoring; review at project completion | Yes | Successful
P172 | RPI | Housing and Meal Planning | Project Management | 2.45 | 1.75 | 0.143 | 4.2875 | 0.61311 | Low | Accept with monitoring; review at project completion | Yes | Successful
P191 | RPI | Collaboration Tool | Project Management | 2.45 | 1.75 | 0.143 | 4.2875 | 0.61311 | Low | Accept with monitoring; review at project completion | Yes | Successful
P055 | RPI | Network services | Project Management | 2.82 | 1.5 | 0.143 | 4.23 | 0.60489 | Low | Accept with monitoring; review at project completion | Yes | Delayed
P089 | RPI | Tax reporting | Project Management | 2.82 | 1.5 | 0.143 | 4.23 | 0.60489 | Low | Accept with monitoring; review at project completion | No | Delayed
P175 | RPI | Financial modeling and reporting; forecasting | Project Management | 2.82 | 1.5 | 0.143 | 4.23 | 0.60489 | Low | Accept with monitoring; review at project completion | No | Delayed
P008 | RPI | Image Design and Creativity Tool | Project Management | 2.09 | 2 | 0.143 | 4.18 | 0.59774 | Low | Accept with monitoring; review at project completion | Yes | Successful
P171 | RPI | Social media management tool that helps brand | Project Management | 3.18 | 1.25 | 0.143 | 3.975 | 0.56842 | Low | Accept with monitoring; review at project completion | Yes | Delayed
P103 | RPI | SSL certificates | Project Management | 2.45 | 1.5 | 0.143 | 3.675 | 0.52553 | Low | Accept with monitoring; review at project completion | No | Successful
P061 | RPI | Development and Alumni TPS | Project Management | 2.45 | 1.5 | 0.143 | 3.675 | 0.52553 | Low | Accept with monitoring; review at project completion | Yes | Successful
P042 | RPI | DNS security | Project Management | 1.73 | 2 | 0.143 | 3.46 | 0.49478 | Low | Accept with monitoring; review at project completion | Yes | Successful
P073 | RPI | RPIAlert emergency notification | Project Management | 3.18 | 1 | 0.143 | 3.18 | 0.45474 | Low | Accept with monitoring; review at project completion | Yes | Delayed
P189 | RPI | Server Virtualization and management | Project Management | 2.09 | 1.5 | 0.143 | 3.135 | 0.4483 | Low | Accept with monitoring; review at project completion | No | Successful
P181 | RPI | Platform for managing search interfaces to sc | Project Management | 2.09 | 1.5 | 0.143 | 3.135 | 0.4483 | Low | Accept with monitoring; review at project completion | Yes | Successful
P099 | RPI | Learning Outcomes and Assessment | Project Management | 2.82 | 1 | 0.143 | 2.82 | 0.40326 | Low | Accept with monitoring; review at project completion | Yes | Delayed
P188 | RPI | Capital Asset Tracking | Project Management | 2.82 | 1 | 0.143 | 2.82 | 0.40326 | Low | Accept with monitoring; review at project completion | Yes | Delayed
P162 | RPI | SSO Authentication | Project Management | 1.36 | 2 | 0.143 | 2.72 | 0.38896 | Low | Accept with monitoring; review at project completion | No | Successful
P102 | RPI | Research Core billing system | Project Management | 1.36 | 2 | 0.143 | 2.72 | 0.38896 | Low | Accept with monitoring; review at project completion | Yes | Successful
P177 | RPI | data visualization software | Project Management | 1.73 | 1.5 | 0.143 | 2.595 | 0.37108 | Low | Accept with monitoring; review at project completion | Yes | Successful
P037 | RPI | Research proposal Mgmt – pre/post award | Project Management | 2.45 | 1 | 0.143 | 2.45 | 0.35035 | Low | Accept with monitoring; review at project completion | No | Successful
P150 | RPI | video and visual communications software | Project Management | 2.45 | 1 | 0.143 | 2.45 | 0.35035 | Low | Accept with monitoring; review at project completion | Yes | Successful
P116 | RPI | Mathematical Computation | Project Management | 2.45 | 1 | 0.143 | 2.45 | 0.35035 | Low | Accept with monitoring; review at project completion | Yes | Successful
P153 | RPI | Authentication services | Project Management | 2.45 | 1 | 0.143 | 2.45 | 0.35035 | Low | Accept with monitoring; review at project completion | Yes | Successful
P148 | RPI | Mail Authenticated Transport | Project Management | 1.73 | 1.25 | 0.143 | 2.1625 | 0.30924 | Low | Accept with monitoring; review at project completion | Yes | Successful
P086 | RPI | Fuel tracking system | Project Management | 1.73 | 1.25 | 0.143 | 2.1625 | 0.30924 | Low | Accept with monitoring; review at project completion | No | Successful
P047 | RPI | Student Government system for club budgeting | Project Management | 2.09 | 1 | 0.143 | 2.09 | 0.29887 | Low | Accept with monitoring; review at project completion | Yes | Successful
P093 | RPI |  | Project Management | 2.09 | 1 | 0.143 | 2.09 | 0.29887 | Low | Accept with monitoring; review at project completion | Yes | Successful
P146 | RPI | Print job management/accounting | Project Management | 1.36 | 1.5 | 0.143 | 2.04 | 0.29172 | Low | Accept with monitoring; review at project completion | No | Successful
P156 | RPI | Development call campaign, RenExchange | Project Management | 1.36 | 1.5 | 0.143 | 2.04 | 0.29172 | Low | Accept with monitoring; review at project completion | No | Successful
P176 | RPI | Budget Planning | Project Management | 1 | 1.75 | 0.143 | 1.75 | 0.25025 | Low | Accept with monitoring; review at project completion | Yes | Successful
R196 | [5 empty] | 0.38 |  | 0 | Low | Accept with monitoring; review at project completion
R197 | [5 empty] | 0.38 |  | 0 | Low | Accept with monitoring; review at project completion
R198 | [5 empty] | 0.38 |  | 0 | Low | Accept with monitoring; review at project completion
R199 | [5 empty] | 0.38 |  | 0 | Low | Accept with monitoring; review at project completion
R200 | [5 empty] | 0.38 |  | 0 | Low | Accept with monitoring; review at project completion
R201 | [5 empty] | 0.38 |  | 0 | Low | Accept with monitoring; review at project completion
R202 | [5 empty] | 0.38 |  | 0 | Low | Accept with monitoring; review at project completion
R203 | [5 empty] | 0.38 |  | 0 | Low | Accept with monitoring; review at project completion
R204 | [5 empty] | 0.38 |  | 0 | Low | Accept with monitoring; review at project completion
R205 | [5 empty] | 0.38 |  | 0 | Low | Accept with monitoring; review at project completion

## Risk Heatmap
Risk Heatmap — ARS Matrix by P × I × β
Each cell = ARS value for that P × I combination at the given β weight. Colour = priority tier. Your dataset β = 0.53 (RM) and 0.31 (PM).
| PM Risks — β = 0.143 (from SEM Weights D8) | [7 empty] | RM Risks — β = 0.380 (from SEM Weights D9)
| P \ I → | I = 1 | I = 2 | I = 3 | I = 4 | I = 5 | Max ARS |  | P \ I → | I = 1 | I = 2 | I = 3 | I = 4 | I = 5 | Max ARS
| P = 5 | 0.715 | 1.43 | 2.145 | 2.86 | 3.575 | 3.575 |  | P = 5 | 1.9 | 3.8 | 5.7 | 7.6 | 9.5 | 9.5
| P = 4 | 0.572 | 1.144 | 1.716 | 2.288 | 2.86 | 2.86 |  | P = 4 | 1.52 | 3.04 | 4.56 | 6.08 | 7.6 | 7.6
| P = 3 | 0.429 | 0.858 | 1.287 | 1.716 | 2.145 | 2.145 |  | P = 3 | 1.14 | 2.28 | 3.42 | 4.56 | 5.7 | 5.7
| P = 2 | 0.286 | 0.572 | 0.858 | 1.144 | 1.43 | 1.43 |  | P = 2 | 0.76 | 1.52 | 2.28 | 3.04 | 3.8 | 3.8
| P = 1 | 0.143 | 0.286 | 0.429 | 0.572 | 0.715 | 0.715 |  | P = 1 | 0.38 | 0.76 | 1.14 | 1.52 | 1.9 | 1.9
ACTUAL ARS DISTRIBUTION IN DATASET (N = 195)
| High (ARS 6–12): 28 projects (14.4%) |  | Moderate (3–6): 93 projects (47.7%) |  | Low (< 3): 74 projects (37.9%) |  | Max ARS in data: 9.394 (P195 — Workday Student, LA Tech) | Mean ARS: 3.805
LEGEND
| Critical |  | ARS > 12 |  | No projects in current dataset at this tier
| High |  | 6.0–12.0 |  | 28 projects (14.4%) — all Delayed; assign risk owners now
| Moderate |  | 3.0–6.0 |  | 93 projects (47.7%) — active monitoring and contingency planning
| Low |  | < 3.0 |  | 74 projects (37.9%) — majority Successful; accept with monitoring

## Project Analysis
Project Analysis — Top 30 Highest ARS Projects
Projects sorted by ARS score (highest risk first). Use this sheet to identify which projects need immediate attention.
Rank | Project ID | Institution | Project Name | Category | P | I | β | ARS | Priority | PM Used | RM Used | Complexity | Outcome | Action Required
1 | P195 | LA Tech | Workday Student | Risk Management | 4.27 | 5 | 0.38 | 8.113 | High | Yes | Yes | High | Delayed | Active mitigation planning required; include in formal risk register
2 | P053 | RPI | Network services | Risk Management | 4.64 | 4.25 | 0.38 | 7.4936 | High | Yes | Yes | High | Delayed | Active mitigation planning required; include in formal risk register
3 | P107 | RPI | Inventions and patents | Risk Management | 3.91 | 5 | 0.38 | 7.429 | High | No | No | High | Delayed | Active mitigation planning required; include in formal risk register
4 | P155 | RPI | Email Spam filter | Risk Management | 4.27 | 4.5 | 0.38 | 7.3017 | High | Yes | Yes | High | Delayed | Active mitigation planning required; include in formal risk register
5 | P049 | RPI | Backups | Risk Management | 3.91 | 4.75 | 0.38 | 7.0576 | High | Yes | Yes | High | Delayed | Active mitigation planning required; include in formal risk register
6 | P010 | RPI | Parking Management System | Risk Management | 4.27 | 4.25 | 0.38 | 6.896 | High | No | No | High | Delayed | Active mitigation planning required; include in formal risk register
7 | P076 | RPI | Payment processing Software (check print | Risk Management | 3.55 | 5 | 0.38 | 6.745 | High | Yes | Yes | High | Delayed | Active mitigation planning required; include in formal risk register
8 | P122 | RPI | Package Tracking System | Risk Management | 3.55 | 5 | 0.38 | 6.745 | High | Yes | Yes | High | Delayed | Active mitigation planning required; include in formal risk register
9 | P136 | RPI | Interlibrary loan and document delivery | Risk Management | 3.55 | 5 | 0.38 | 6.745 | High | No | Yes | High | Delayed | Active mitigation planning required; include in formal risk register
10 | P142 | RPI | Data Warehouse Business Intelligence and | Risk Management | 3.91 | 4.5 | 0.38 | 6.6861 | High | Yes | Yes | High | Delayed | Active mitigation planning required; include in formal risk register
11 | P110 | RPI | Intellectual Property | Risk Management | 5 | 3.5 | 0.38 | 6.65 | High | Yes | Yes | Medium | Failed | Active mitigation planning required; include in formal risk register
12 | P041 | RPI | Wireless network management | Risk Management | 3.55 | 4.75 | 0.38 | 6.4078 | High | Yes | Yes | High | Delayed | Active mitigation planning required; include in formal risk register
13 | P115 | RPI | Major Gift Fundraising Software | Risk Management | 3.91 | 4.25 | 0.38 | 6.3147 | High | Yes | Yes | High | Delayed | Active mitigation planning required; include in formal risk register
14 | P075 | RPI | Alumni collaboration | Risk Management | 3.55 | 4.5 | 0.38 | 6.0705 | High | Yes | No | High | Delayed | Active mitigation planning required; include in formal risk register
15 | P158 | RPI | *Need description from Bursar office* | Risk Management | 3.91 | 4 | 0.38 | 5.9432 | Moderate | Yes | Yes | High | Delayed | Active mitigation planning required; include in formal risk register
16 | P161 | RPI | Comromised account reporting service | Organizational Readiness | 3.18 | 4.75 | 0.38 | 5.7399 | Moderate | Yes | Yes | High | Delayed | Active mitigation planning required; include in formal risk register
17 | P026 | RPI | Benefits management. Employee & HR Porta | Risk Management | 3.55 | 4.25 | 0.38 | 5.7332 | Moderate | Yes | Yes | High | Delayed | Active mitigation planning required; include in formal risk register
18 | P112 | RPI | Procurement messaging connector | Risk Management | 3.55 | 4.25 | 0.38 | 5.7332 | Moderate | Yes | No | High | Delayed | Active mitigation planning required; include in formal risk register
19 | P159 | RPI | Customer communication platform for tran | Risk Management | 3.55 | 4.25 | 0.38 | 5.7332 | Moderate | No | No | High | Delayed | Active mitigation planning required; include in formal risk register
20 | P006 | RPI | Digital asset management system | Risk Management | 4.27 | 3.5 | 0.38 | 5.6791 | Moderate | No | No | High | Delayed | Active mitigation planning required; include in formal risk register
21 | P096 | RPI | Internships and job placement | Risk Management | 4.27 | 3.5 | 0.38 | 5.6791 | Moderate | Yes | Yes | High | Delayed | Active mitigation planning required; include in formal risk register
22 | P015 | RPI | Digital asset management system for arch | Risk Management | 3.91 | 3.75 | 0.38 | 5.5718 | Moderate | No | Yes | High | Delayed | Active mitigation planning required; include in formal risk register
23 | P019 | RPI | Logging attendance at events with ID Car | Risk Management | 3.55 | 4 | 0.38 | 5.396 | Moderate | No | No | High | Delayed | Active mitigation planning required; include in formal risk register
24 | P135 | RPI | Web Proxy service | Risk Management | 3.55 | 4 | 0.38 | 5.396 | Moderate | No | No | High | Delayed | Active mitigation planning required; include in formal risk register
25 | P121 | RPI | Weather Sentry system | Risk Management | 4.64 | 3 | 0.38 | 5.2896 | Moderate | No | No | Medium | Delayed | Active mitigation planning required; include in formal risk register
26 | P095 | RPI | Secondary authoritative DNS (external) | Risk Management | 4.27 | 3.25 | 0.38 | 5.2734 | Moderate | Yes | Yes | Medium | Delayed | Active mitigation planning required; include in formal risk register
27 | P151 | RPI | Health Center software | Risk Management | 3.91 | 3.5 | 0.38 | 5.2003 | Moderate | Yes | Yes | Medium | Delayed | Active mitigation planning required; include in formal risk register
28 | P192 | RPI | Project Management | Risk Management | 3.91 | 3.5 | 0.38 | 5.2003 | Moderate | No | No | Medium | Delayed | Active mitigation planning required; include in formal risk register
29 | P101 | RPI | Imaging and Document Management, Workflo | Organizational Readiness | 3.18 | 4.25 | 0.38 | 5.1357 | Moderate | Yes | No | High | Delayed | Periodic monitoring; develop contingency plan at next milestone
30 | P091 | RPI | because Microsoft Live is not effective | Organizational Readiness | 2.82 | 4.75 | 0.38 | 5.0901 | Moderate | No | Yes | High | Delayed | Periodic monitoring; develop contingency plan at next milestone

## Formula Reference
ARS Formula Reference & Methodology Documentation
| THE FORMULA | ARS = P × I × β
| VARIABLE | DEFINITION
| P — Probability | Likelihood of risk occurring (1–5). In this study derived from Risk_Score_Normalized (0–100) scaled to 1–5.
| I — Impact | Severity of consequences (1–5). Derived from project Complexity and risk weighting components, scaled to 1–5.
| β — SEM Weight | Standardized path coefficient from IBM AMOS. β = 0.53 for RM→IS (placeholder; update after AMOS run). Reflects empirically-validated causal importance of construct on Implementation Success.
| ARS | Adjusted Risk Score. Higher ARS = higher institutional priority. Grounded in SEM causal theory rather than expert judgment alone.
| PRIORITY TIERS | CLASSIFICATION & DATASET COUNTS
| ARS > 12.0 | CRITICAL — Immediate mitigation. Count in dataset: 0 (0.0%)
| ARS 6.0–12.0 | HIGH — Active mitigation required. Count in dataset: 28 (14.4%)
| ARS 3.0–6.0 | MODERATE — Periodic monitoring. Count in dataset: 93 (47.7%)
| ARS < 3.0 | LOW — Accept with monitoring. Count in dataset: 74 (37.9%)
| RM INDICATOR DERIVATION | HOW RM1, RM2, RM3 ARE DERIVED FROM ARS
RM1 — Identification
RM2 — Assessment
RM3 — Mitigation
| KEY CITATIONS | ARS formula: Chapter 3 Section 3.5.4. β weights: Chapter 4 Table 4.9. RM derivation: Dataset v2 Conversion Documentation. PMI PMBOK 7th Ed. ISO 31000. Selvakumar et al. (2024). de Bakker et al. (2010). Goswami (2024).